## Sheet1
Green numbers are actual values added over time by you
Black numbers are initial planning input from you
Red numbers are calculated automatically
Blue numbers are standards/goals
Development Phase | Planned Defect Injection Rate (D/Hr) | Actual Defect Injection Rate (D/Hr) | Planned Defect Removal Yield | Actual Defect Removal Yield | Planned Defects Injected | Planned Defects Removed | Planned Total Remaining Defects | Phase | Planned Project Code Size in KLOC | Planned Defects per KLOC (after phase done) | "Reason-able" Dfts/KLOC | Actual Defects Injected (known so far) | Actual Defects Found & Removed | Estimated Remaining Defects (simplistic) | Actual Defects per KLOC after phase | Actual Code Size in KLOC
Requirements | 0.25 | #DIV/0! |  |  | 2.5 | 0 | 2.5 | Req |  |  |  | 0 | 0 | 0
Req. Inspection |  |  | 0.7 | #DIV/0! | 0 | 1.75 | 0.75 | Req. Insp |  |  |  | 0 | 0 | 0
Analysis | 0.25 | #DIV/0! |  |  | 2.5 | 0 | 3.25 | Anal |  |  |  | 0 | 0 | 0
Analysis Inspection |  |  | 0.7 | #DIV/0! | 0 | 2.275 | 0.975 | Anal Insp |  |  |  | 0 | 0 | 0
Design | 2 | #DIV/0! |  |  | 40 | 0 | 40.975 | Design |  |  |  | 0 | 0 | 0
Design Inspection |  |  | 0.7 | #DIV/0! | 0 | 28.6825 | 12.2925 | Design Insp |  |  |  | 0 | 0 | 0
Code | 4 | #DIV/0! |  |  | 80 | 0 | 92.2925 | Code | 1.25 | 73.834 |  | 0 | 0 | 0 | #DIV/0! | 0
Compile/Indiv Review |  |  | 0.7 | #DIV/0! | 0 | 64.6047 | 27.6878 | Comp/iRev |  | 22.1502 | <5 | 0 | 0 | 0 | #DIV/0!
Unit Test |  |  | 0.9 | #DIV/0! | 0 | 24.919 | 2.7688 | Unit Test |  | 2.215 | <0.5 | 0 | 0 | 0 | #DIV/0!
System Test |  |  | 0.8 | #DIV/0! | 0 | 2.215 | 0.55376 | System Test |  | 0.443 |  | 0 | 0 | 0 | #DIV/0!
|  |  |  | Total Defects | 125 | 0 | Actual Total Defects |  |  |  |  | Removed=Injected: | 0
|  |  |  | Total Defects/KLOC | 100 | #DIV/0! | Actual Total Defects/KLOC
|  |  |  | "Reasonable" Total Defects/KLOC | 100–200
Tasks/Work Units | Planned Time | Actual Time | Planned Size | Units | Actual Size |  |  |  | Useful Stats | Planned | Actual | Standard
Req Doc | 10 | 0 | 10 | pages | 0 |  |  |  | LOC/Hour | 62.5 | #DIV/0!
Req inspect | 0.5 | 0 | [6 empty] | DEFECTS/PAGE
SAD | 10 | 0 | 15 | pages | 0 |  |  |  | Req | 0.25 | #DIV/0!
SAD inspect | 0.5 | 0 | [6 empty] | Anal | 0.16667 | #DIV/0!
Design | 20 | 0 | 25 | pages | 0 |  |  |  | Detailed design | 1.6 | #DIV/0!
Design inspect | 0.5 | 0 | [6 empty] | DEFECT RATIOS
Coding | 20 | 0 | 1250 | LOC | 0 |  |  |  | DesignRev/UnitTest | 1.151 | #DIV/0! | >2.0
Compile/Review | 0.25 | 0 | [6 empty] | DEVELOPMENT TIME RATIOS
Unit Testing | 1 | 0 | [6 empty] | Req inspect / Req | 0.05 | #DIV/0! | >0.25
System Test | 1 | 0 | [6 empty] | Anal Inspec / Anal | 0.05 | #DIV/0! | >0.5
[9 empty] | Design / Coding | 1 | #DIV/0! | >1.0
[9 empty] | Design Rev/Design | 0.025 | #DIV/0! | >0.5
[9 empty] | Code Review/Code | 0.0125 | #DIV/0! | >0.5
[9 empty] | Appraisal/Failure | 0.66667 | #DIV/0! | >1.0
REVIEW RATES
[9 empty] | Req pg/hr | 20 | #DIV/0! | <2
[9 empty] | Anal pg/hr | 1.5 | #DIV/0! | <5
[9 empty] | Design pg/hr | 1.25 | #DIV/0!
[9 empty] | Code LOC/hr | 62.5 | #DIV/0! | <200
Note on A27: Keith Decker: ESSENTIALLY, this is your existing TASK spreadsheet.
Note on O5: Keith Decker: There are better ways to esitmate the remaining defects (I.e. finding one bug indicates that there may be more of them). We may discuss the "capture/recapture" statistical approach to this.